## Slide 1
VALUE CONSULTING · PDP · INTERNAL
Product Factory:
from concept to revenue
The execution plan for four paid product wedges that pre-install Banking OS,
make the function cost neutral inside a year, and open a recurring revenue line.
Shyam · July 2026 · prepared for the talent programme (Tim Ruttner) and the PDP track (Mayur)
One product in market
by January 2027.
Four sellable SKUs and a recurring
line by mid 2027.

## Slide 2
1
01 · CHAPTER
The frameworks
The thesis, the product filter, the economics, the lifecycle, and the pod that runs it.

## Slide 3
FRAMEWORKS · THE THESIS
Every product earns a fee, harvests the bank’s reality, and installs the first component of Banking OS.
1
Filter rule: a candidate that fails any one of the three tests is consulting, and stays out of the product line. Aligned to the Banking OS canon (knowledge/product/banking-os.md).
Test 1 · It earns a fee
Each install is paid work at €15-100K, priced as a product with a fixed scope and a delivery kit.
Test 2 · It harvests proprietary data
The engagement captures the bank’s real processes, data structures and policies. Evidence only Backbase holds.
Test 3 · It pre-binds a Banking OS layer
The output is a working component: Nexus, Sentinel or a Mission candidate, already present in the account.
THE ONE-LINER
Paid discovery that leaves the platform installed.
Each engagement ends with a live Banking OS component in the account, a quantified expansion case for the AE, and account intelligence competitors and SIs never see.
Notes: The three-part design filter from the 29 Jun PDP session. Product-proximate = moat; customer-proximate = competitive space we lose. Every SKU must pass all three tests.

## Slide 4
FRAMEWORKS · THE ECONOMICS
Ten paid installs a year cover the full team cost; every install beyond is new revenue.
1
Package = Assess & Solution €60K + Mission POC €60K. Team cost of ~€1.2M a year is the PDP working figure and is to be validated with finance. Year-two target of 14-16 installs is a planning range.
Installs to cost neutrality (10)
Year-two expansion range (14-16)
10
installs a year at an average package of €120K cover the ~€1.2M annual team cost.
Notes: Cost-neutrality is the floor, revenue generation is the objective. 10 × €120K ≈ €1.2M. Year two adds recurring Value Telemetry revenue on top of installs.

## Slide 5
FRAMEWORKS · THE LADDER
The wedge stays free; depth and recurrence carry the price.
1
Recurring range is a target shape anchored on SAP and ServiceNow success-plan pricing of 10-30% of licence value, and on FinOps gain-share market practice (15-35% of realised savings).
Rung 0 · free wedge
Ignite Inspire
~4 meetings, benchmark and use-case shortlist. Grows the funnel.
→
Assess & Solution
€60K
Mission POC
€60K
Rungs 1 + 2 · the €120K package (to scale)
→
Rung 3 · recurring
Value Assurance
€30-50K a year + gain share
The free wedge feeds the funnel
Four meetings surface the leakage evidence that qualifies the paid wedge. Zero friction to start.
Recurrence is the growth flywheel
Telemetry converts every live deployment into quarterly revenue that compounds with AI consumption.
Notes: Rung 0 free = funnel. Rungs 1+2 = the €120K SKVC package = cost neutrality. Rung 3 = the growth flywheel (Value Telemetry + gain-share).

## Slide 6
FRAMEWORKS · THE LIFECYCLE
One motion carries every product from concept to installed platform.
1
Durations are per-engagement figures once the product is built, with a ±30% planning tolerance. The first pass through stages 1-4 is the one-time product build.
01
Concept
VC · 1 wk
→
02
Design
VC + SE · 1-2 wks
→
03
Prototype
SE · 2-3 wks
→
04
Proof
VC · 2-4 wks
→
05
Proposal
VC + AE · 1 wk
→
06
Signature
AE + VC · 2-4 wks
→
07
Install
FDE + SE · 6-12 wks
The lifecycle runs twice over.
The first pass through stages 1-4 builds the product itself. From the second account onward, the same motion runs as a 4-8 week sales-and-delivery cycle per install.
Notes: Stage exit gates: Concept = qualified sponsor + pain. Design = signed SoW, agreed metrics, data access. Prototype = working demo on the client’s own data. Proof = CFO-grade evidence pack. Proposal = commercial offer + named Mission candidate. Signature = signed order form. Install = layer live + expansion roadmap handed to the AE.

## Slide 7
FRAMEWORKS · RESOURCING
A pod of two and a half people runs the whole line; hiring follows revenue.
1
FTE figures are steady-state allocations during build and delivery phases; FDE capacity is drawn from standard Mission Sprint staffing at install, so it is charged to the delivery, and not to this pod.
You · product owner · 1.0 FTE
SKU design, value narrative, proof economics, proposal. Owns the P&L of the line.
Solution engineer · 0.5 FTE, named
Connectors, data extraction, Factory tooling at prototype and install. The technical spine.
FDE · on demand at install
Runs the Factory Mission Sprint once an install is signed. 6-12 weeks per Mission.
SME · on call
Risk and compliance review for Guardrail Studio; R&D liaison for the Cartographer.
WHY THE SOLUTION ENGINEER MATTERS
One named SE across all four products, so skill compounds.
Every product runs on the same Factory tools: Connector Studio, Semantic Modeler, Simulation & Testing. Each install makes the next one cheaper and faster to deliver.
Notes: This is an allocation ask, and specifically NOT a hiring ask. The SE is the critical unlock: same person across all four products so tooling skill compounds.

## Slide 8
FRAMEWORKS · THE OBJECTIONS
The three obvious objections have concrete answers.
1
AIB reference: paid an estimated ~€80K for an external current/future-state assessment (ADS), PDP session record, 29 Jun 2026. Wedge pattern references: AWS OLA, SAP Outside-In, ServiceNow Inspire.
“Banks will not pay for discovery.”
The market already does: AIB paid ~€80K for a weaker assessment. AWS, SAP and ServiceNow all run the diagnostic-wedge motion; ours goes further by installing product.
“We have no capacity to build products.”
Build effort is 6-12 person-weeks per product because the Factory tools, the APA V3 catalog and the cost model already exist. The sequence builds one product at a time.
“This distracts from platform sales.”
Every install pre-binds Nexus, Sentinel or a Mission and hands the AE a quantified expansion case. The wedge is the land motion of land-and-expand.
Notes: Use these in the Tim and Mayur conversations. Each answer is evidence-backed, from the PDP research.

## Slide 9
1
02 · CHAPTER
Four execution plans
Product by product: milestones, effort, pod, ticket, and the gate that unlocks each one.

## Slide 10
EXECUTION PLAN 1 OF 4 · PROCESS X-RAY
Process X-Ray ships first: demo by October, paid proof by December, first revenue in January.
1
Effort carries a ±30% tolerance. Build is low-risk because the APA V3 catalog (65 processes, 283 steps), the journey builder and the value-leakage method already exist in the repo.
Aug 2026
Design
Delivery kit, pricing one-pager, demo script. 3 pw, VC.
Sep-Oct 2026
Prototype
Demo on the APA V3 catalog (65 processes) plus one friendly dataset. 5 pw, SE-led.
Oct 2026
Pilot gate
Prospect pilot green-light with Mayur. AIB-profile account.
Oct-Dec 2026
Proof
Paid pilot: leakage heatmap, top-3 Mission candidates with ROI evidence. 6 pw.
Jan 2027
First signature
Wedge sold at €50-75K; install starts as a Factory Mission Sprint.
BUILD EFFORT
8-10 person-wks
DELIVERY PER INSTALL
4-6 wks · 12-14 pw
POD
VC 1.0 + SE 0.5
PRE-BINDS
Mission candidate + ROI
Notes: X-Ray productizes the Process & Workspace Designer. It observes real flows across the 6-12 systems per journey and quantifies leakage in the messy middle, where ~60% of bank work lives.

## Slide 11
EXECUTION PLAN 2 OF 4 · VALUE TELEMETRY
Value Telemetry rides the keystone cost-per-outcome model and opens the recurring line.
1
Gain-share pricing of 15-35% of realised savings is market-validated (ProsperOps, nOps, Vantage), with a “10% or free” floor. Current cost-model sample is n=2 use cases; the keystone study raises it to ~5.
Sep 2026
Keystone gate
Extend the cost model from cost-per-interaction to cost-per-outcome, with Deepak. ~5 use cases.
Sep 2026
Design
SKU spec: diagnostic scope, telemetry set, gain-share terms. 4 pw, VC.
Oct 2026
Prototype
Cost-per-outcome dashboard on one live deployment’s data. 3 pw.
Nov-Dec 2026
Proof
2-3 week diagnostic at a live customer: waste quantified, ROI re-proved. 3 pw.
Jan 2027
First signature
€15-50K diagnostic + 15-35% gain share; quarterly recurrence begins.
BUILD EFFORT
6-8 person-wks
DELIVERY PER INSTALL
2-3 wks · 3-4 pw
POD
VC 0.5 + SE 0.25
MODEL
Recurring + gain share
Notes: This is backlog item 2.2 (keystone, do first) + 2.3 (the SKU). Partner with Aayushi on the value-assurance line. Only Backbase sees cost-per-resolved-outcome; external FinOps tools see the cloud bill.

## Slide 12
EXECUTION PLAN 3 OF 4 · GUARDRAIL STUDIO
Guardrail Studio attaches to every Conversational Banking deal in flight.
1
Timed to the Conversational Banking pipeline: Transact and Resolve capabilities require governed execution, which makes the Sentinel-readiness wedge a natural attach on active deals.
Jan 2027
Design
Decision & Policy tooling alignment; risk and compliance SME briefed. 3 pw.
Feb-Mar 2027
Prototype
Authority-map demo: recommend, approve, execute per process. 5 pw.
Apr-May 2027
Proof
Paid pilot: guardrail backlog, entitlements map, Sentinel install blueprint. 6 pw.
Jun 2027
First signature
Sold at €50-100K, riding Transact and Resolve deals in flight.
BUILD EFFORT
8-10 person-wks
DELIVERY PER INSTALL
5-6 wks · 8-10 pw
POD
VC 1.0 + SE 0.5 + SME 0.2
PRE-BINDS
Sentinel
Notes: Guardrail Studio productizes Decision & Policy. It codifies authority, policies, entitlements and audit needs into executable guardrails, and the output is the Sentinel deployment blueprint.

## Slide 13
EXECUTION PLAN 4 OF 4 · ONTOLOGY CARTOGRAPHER
Ontology Cartographer is the deepest build and lands where X-Ray has created demand.
1
Sequenced last deliberately: it has the highest technical depth, needs R&D alignment, and sells best into accounts where an X-Ray install has already evidenced the cost of fragmented data.
Feb 2027
R&D gate
Alignment with the Semantic Modeler and Nexus teams on tooling reuse.
Mar-Apr 2027
Prototype
Ontology mapping demo on two sample cores (core, CRM, LMS, credit). 6 pw, SE-led.
May-Jul 2027
Proof
Paid pilot: ontology coverage map, data-to-truth gap report, Nexus blueprint. 8 pw.
Aug 2027
First signature
Sold at €75-100K, attached to Relationship Intelligence opportunities.
BUILD EFFORT
10-12 person-wks
DELIVERY PER INSTALL
6-8 wks · 12-16 pw
POD
SE 1.0 + VC 0.5 (SE-led)
PRE-BINDS
Nexus
Notes: Cartographer productizes the Semantic Modeler. Relationship Intelligence (Grow plays, share of wallet) requires shared truth, so every RI opportunity is a Cartographer prospect.

## Slide 14
EXECUTION PLANS · THE REGISTER
Twelve months of product build fits inside the existing pod.
1
pw = person-weeks. Build = one-time productization effort. Delivery = elapsed and effort figures per client install once productized. All efforts carry a ±30% planning tolerance.
PRODUCT
ONE-TIME BUILD
DELIVERY PER INSTALL
POD
FIRST REVENUE
Process X-Ray
8-10 pw
4-6 wks · 12-14 pw
VC 1.0 + SE 0.5
Jan 2027
Value Telemetry
6-8 pw
2-3 wks · 3-4 pw
VC 0.5 + SE 0.25
Jan 2027
Guardrail Studio
8-10 pw
5-6 wks · 8-10 pw
VC 1.0 + SE 0.5 + SME
Jun 2027
Ontology Cartographer
10-12 pw
6-8 wks · 12-16 pw
SE 1.0 + VC 0.5
Aug 2027
Notes: Total build load Aug 2026 - Jul 2027: 32-40 person-weeks across four products, sequenced so the pod never carries two builds at once.

## Slide 15
1
03 · CHAPTER
Mobilization and the ask
The twelve-month sequence, how the Delivery Factory carries it, and the four decisions that unlock it.

## Slide 16
MOBILIZATION · THE SEQUENCE
One product at a time reaches four sellable SKUs and recurring revenue inside twelve months.
1
Red diamonds are decision gates (SE named · pilot green-light · R&D alignment). Blue diamonds mark first revenue per product. Bars show elapsed calendar time, and effort within them is per the register.
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
Jun
Jul
2026
2027
Keystone study
With Deepak
Process X-Ray
Prototype
Proof
Sell + install
Value Telemetry
Proof
Recurring
Guardrail Studio
Prototype
Proof
Sell
Ontology Cartographer
Prototype
Proof
Notes: Sequencing logic: X-Ray first (lowest build risk, front-door product), Telemetry parallel (shares the keystone cost model work), Guardrail rides the Conversational pipeline, Cartographer lands on X-Ray demand.

## Slide 17
MOBILIZATION · THE DELIVERY FACTORY
The Delivery Factory carries every stage from prototype to installed layer.
1
Factory toolchain per the Banking OS canon: Process & Workspace Designer · Semantic Modeler · Agent Builder · Decision & Policy · Connector Studio · Simulation & Testing · Deployment & Ops Control.
PROTOTYPE
Semantic Modeler +
Connector Studio
A working demo on the bank’s own data, in weeks.
→
PROOF
Simulation & Testing +
Ops Control telemetry
CFO-grade evidence runs with zero production risk.
→
INSTALL
Mission Contract with
Nexus + Sentinel binding
The Banking OS layer live in 6-12 weeks, via the agentic SDLC.
→
RUN
Deployment &
Ops Control
Live telemetry that feeds Value Telemetry and the expansion case.
Notes: The insight from the PDP session: the Factory already contains the discovery-end tools. The products ARE those tools, productized as standalone paid wedges. Delivery cost stays at person-weeks because nothing is built from scratch.

## Slide 18
MOBILIZATION · THE ASK
Four decisions unlock execution; the €5,000 talent budget seeds product number one.
1
Quota figure of ~€200K recognition and pilot-account choice are open PDP items (1.3, 1.4) for the next 1:1 with Mayur. Keystone study scope sits with Deepak (backlog item 2.2).
1 · Name the solution engineer
0.5 FTE from the regional pool, committed by September. The single critical-path resource.
2 · Green-light one prospect pilot
AIB-profile account for the X-Ray proof, by October. A prospect, keeping existing customers out of scope.
3 · Back the keystone study
Cost-per-outcome model with Deepak in September. Value Telemetry and the FinOps line depend on it.
4 · Agree the commercial treatment
Quota recognition of ~€200K so the line carries a real target from day one.
THE €5,000 SEED
The talent budget launches product number one.
Packaging and delivery kit for Process X-Ray, a demo built on the APA V3 catalog, launch collateral produced with marketing, and pricing pressure-tests with three friendly accounts.
Notes: Framing for Tim: the talent budget becomes seed capital for a product launch, and specifically not a training spend. Framing for Mayur: these four asks are the same asks already on the PDP backlog.

## Slide 19
MOBILIZATION · PLANNING BASIS
The plan stands on five explicit assumptions, each with an owner to validate.
1
Confidence ratings follow the repo standard: every assumption is documented, conservative, and sensitivity-tested before any figure becomes client-facing or budget-committed.
Team cost ~€1.2M a year
PDP working figure
Low
Validate: Mayur + finance
Effort estimates within ±30%
Analogous VC engagements; first product build actuals will recalibrate
Medium
Validate: First build
SE at 0.5 FTE is available
Regional pool capacity, unconfirmed
Low
Validate: SE leadership
Tickets of €15-100K clear the market
AIB paid ~€80K for a weaker ADS; SAP and AWS wedge benchmarks
Medium
Validate: First 3 deals
Wedge-to-Mission attach of 50%+ in 6 months
SAP and ServiceNow expansion patterns
Low
Validate: Pilot cohort
Notes: Per CLAUDE.md governance: no hidden assumptions. These five carry the plan; validating the first three in September de-risks the whole sequence.

## Slide 20
THE MOTION
Land fast. Prove value.
Expand.
One product in market by January. Cost neutral inside year one.
Four installed-platform wedges and a recurring line by mid 2027.
This week · book the Mayur 1:1: quota treatment, pilot green-light, SE allocation.
This week · follow up with Tim: category story, launch collateral, talent-budget plan.
September · scope the keystone cost-per-outcome study with Deepak.
1